Budget Tracking:

|  | Task Description | Hours |
| --- | --- | --- |
| 2/24/21 - 3/2/21 | Phase 1: Part 1: Discovery Documents | ($60/HR) |
| Jeanna Brault, PM | Audience Analysis | 4:30 |
| Ashley Giedd, CL | Competitive Analysis: > Industry Info, Grid Overview, Appendix Notes, Overall Rating | 3:00 |
| Riandria Gordon, PR | Competitive Analysis: > Summary, Approach, Competitive Overview, Recommendations | 3:00 |
| Sabrina Larson, WPS | Client Survey | 4:30 |
|  | Subtotal Work Hours | 15:00 |
|  | Actual Cost | $900 |
| 3/3/21 - 3/9/21 | Phase 1: Part 2: Clarification Documents |  |
| Jeanna Brault, PM | Creative Brief > Target Audience, Goals | 1:30 |
| Ashley Giedd, CL | Creative Brief > Competitive Positioning, Goals, Statement Overview | 1:00 |
| Riandria Gordon, PR | Creative Brief > Creative Tone | 1:30 |
| Sabrina Larson, WPS | Creative Brief > Statement Overview, Mission Statement, Goals, Target Message | 1:00 |
|  | Subtotal Work Hours | 5:00 |
|  | Actual Cost | $300 |
| 3/10/21 - 3/30/21 | Phase 1: Part 3: Project Planning Documents |  |
|  | Project Scope | 5:00 |
|  | Detailed Schedule | 5:00 |
|  | Detailed Budget | 6:00 |
|  | Work Breakdown Structure Document | 6:00 |
|  | Subtotal Work Hours | _ |
|  | Estimated Work Hours | 22:00 |
|  | Additional Fees, Costs, & Materials |  |
|  | Contract Fee | $80 |
|  | Estimated Cost | $1400 |
|  | Actual Cost | _ |
| 3/31/21 - 4/6/21 | Phase 2: Develop Site Structure |  |
| Jeanna Brault, PM | Site Map, Navigational Structures Plan, Naming and Labeling Plan | 4:00 |
| Sabrina Larson, WPS | Content Outline and Delivery Plan and Naming Conventions Plan | 2:00 |
| Ashley Giedd, CL | Wireframe | 3:00 |
| Riandria Gordon, PR | Key User Paths and User Scenarios | 2:10 |
|  | Subtotal Work Hours | 11:10 |
|  | Estimated Work Hours | 11:10 |
|  | Estimated Cost | $840 |
|  | Actual Cost | _ |
| 4/7/21 - 4/13/21 | Phase 3: Design Virtual Interface |  |
|  | Templates and Mockups | 18:30 |
|  | Style Guidelines | 12:00 |
|  | User Experience | 2:00 |
|  | Functionality and Flow Confirmation | 2:00 |
|  | Subtotal Work Hours | 34:30 |
|  | Estimated Work Hours | 18:00 |
|  | Estimated Cost | $1080 |
|  | Actual Cost | $2070 |
| 4/14/21 - 4/27/21 | Phase 4: Development |  |
|  | Develop Website Content | 8:00 |
|  | Build Responsive Web Design | 6:00 |
|  | Develop Security Features | 3:00 |
|  | Search Engine Optimization | 2:00 |
|  | Markup (Code) | 1:00 |
|  | Subtotal Work Hours | 25:00 |
|  | Estimated Work Hours | 20:00 |
|  | Estimated Cost: | $1200 |
|  | Actual Cost | $1500 |
| 4/14/21 - 4/27/21 | Phase 5: Site Announcement & Final Steps |  |
|  | Site Testing | 4:00 |
|  | Quality Assurance | 3:30 |
|  | Maintenance & Evaluation Plan | 2:00 |
|  | Client Training | 2:00 |
|  | Subtotal Work Hours | 11:30 |
|  | Estimated Work Hours | 10:00 |
|  | Estimated Cost: | $600 |
|  | Actual Cost | $690 |
|  | Additional Costs |  |
|  | Domain Name Registration | $20/year |
|  | Search Engine Registration | $1000 |
|  | Server Hosting | $20/month |
|  | Additional Markup | $1204 |
|  | Additional Upfront Cost | $2244 |
|  | Estimated Total Budget | $8264 |