(03/30/2020)

# Project Scope Plan

PREPARED FOR:

The Nail Hive

PREPARED BY:

Sabrina Larson | Jeanna Brault |Ashley Griedd |

Riandria Gordon

Contents

Mission Statement:	4

Project Goals:	4

Objective Statements:	5

Schedule Overview:	6

Budget Overview:	6

Details and Expectations:	7

Project Standards:	7

Client Responsibility:	7

Design and Developer Responsibility:	7

Agreement of  Terms and Conditions:	9

Invoicing	9

Maintenance and Rates:	10

Web Hosting and Domain:	10

Changes:	10

Completion Date:	10

Payment:	10

Assignment of Project:	11

Copyright and Trademarks:	11

Budget Tracking:	11

Copyrights of Website:	11

Agreement:	12

Appendix:	13

Detailed Schedule:	13

WBS (Work Breakdown Structure Detailed):	15

Detailed Budget:	20

Creative Brief:	24

∙	Statement Overview	24

∙	Mission Statement:	24

∙	Target Audience Profile	24

∙	Competitive Position	25

∙	Creative Tone	25

∙	Target Message	25

∙	Goals	25

# Mission Statement:

Our mission is to establish a business website that represents the Nail Hive’s salon services and displays the Nail Hive’s brand commitment to luxury and relaxation. The site will connect visitors from Facebook and Instagram to expand the Nail Hive’s online presence and customer growth. It will provide visitors with a responsive and user-friendly website experience.

# Project Goals:

- Showcase the Nail Hive’s offered services and brand quality.

- Drive traffic from Facebook and Instagram visitors.

- Increase unique customer site visits.

- Create a responsive, user-friendly website design.

# Objective Statements:

- Establish a business website for the Nail Hive consisting of 4-8 pages to be launched in May 2021.

- Implement a photo gallery of examples of service, featuring nail art and select photos from the Nail Hive’s social media, of three to five web optimized images.

- Implement a photo gallery of pictures of the Nail Hive’s business interior, including three to six web optimized images.

- Present a list of offered services including cost, provided by the Nail Hive.

- Create a “Specials/Deals” page to promote exclusive offers.

- Create a contact page and implement a contact form, detailing the Nail Hive’s contact information and including a question/comment form field.

- Implement an online booking form, linked via call-to-action buttons to ensure an optimal number of clicks.

Strike out items indicate changes made by client request.

# Schedule Overview:

| Phase | Start | End | Work: |
| --- | --- | --- | --- |
| Phase 1 | 2/24/21 | 3/30/21 | Discovery & Overview |
| Phase 2 | 3/31/21 | 4/6/21 | Develop Website Structure |
| Phase 3 | 4/7/21 | 4/13/21 | Design Visual Interface |
| Phase 4 | 4/14/21 | 4/27/21 | Development |
| Phase 5 | 4/28/21 | 5/4/21 | Site Announcement & Final Review |

# Budget Overview:

Budget Phase Overview:

Our hourly wage is $60 an hour per certified professional on the project (4 of us in total). You will be charged for each Hour that each certified professional service on the Design. Each Design incorporates 50 pictures and extra charges made without referring to the customer about it. No undisclosed fees!

Budget Overview:

| Phase: | Work: | Estimated Cost: |
| --- | --- | --- |
| Phase 1 | Discovery & Overview | $2600 |
| Phase 2 | Develop Website Structure | $840 |
| Phase 3 | Design Visual Interface | $1080 |
| Phase 4 | Development | $1200 |
| Phase 5 | Site Announcement & Final Review | $600 |
|  | Additional Costs | $2244 |
|  | Discount | 10% |
|  | Sales Tax | 5% |
| Estimated Total Budget: $8092.35 |  |  |

Maintenance Overview:

| Scheduled Maintenance | Estimated Cost |
| --- | --- |
| Monthly | $90 |
| Quarterly | $120 |
| Yearly | $60 |
| Estimated Yearly Cost | $1620 |
| Cost Per Month | $135 |

# Details and Expectations:

## Project Standards:

- J.A.R.S is hired to create one website for the Nail Hive.

- Create a  website and have it launched by May 2021.

- The website will be compatible with most browsers.

## Client Responsibility:

- Must meet all due dates unless notice is given prior.

- Client will provide text content in a Word document in .doc or .docx format.

- The client will provide images and graphics in either .jpg or .png format.

- Change requests form must be submitted before any changes are to be made.

## Design and Developer Responsibility:

- Must communicate with the client at least once a week.

- The site will pass through CSS, HTML5, and accessibility validation.

- Responsive Design is used to make site content viewable on mobile and desktop.

- If the J.A.R.S team misses the due date, they must inform the client five to seven days prior.

By signing this, you agree and understand the terms above:

X______________________________________________

Customer Print Name

X____Rosalind Scott Owner of the Nail Hive___________    03/30/21

Customer Signature                                                                                   Date

X____JARS WEB DESIGN___________________________    03/30/21

J.A.R.S. Web Design Signature					Date

# Agreement of  Terms and Conditions:

The Nail Hive (Customer) is hiring J.A.R.S. Web Design for a whole project of developing one website to be established on the customer's web hosting server. As an outcome, the client authorizes J.A.R.S. Web Design to access this hosting account and acknowledges the web hosting service to offer us the customer's web page directory and any other directories or programs that might need to edit this project.

## Invoicing

| Invoice | Description | Hours | Rate/Hour | Amount |
| --- | --- | --- | --- | --- |
| INVOICE NUMBER 00001 DATE OF ISSUE 03/30/2021 | Phase 1 | 42 | $60 | $2600 |
|  | Phase 2 | 14 | $60 | $840 |
|  | Phase 3 | 18 | $60 | $1080 |
|  | Phase 4 | 20 | $60 | $1200 |
|  | Phase 5 | 10 | $60 | $600 |
|  | Additional Costs |  |  | $2244 |
|  |  |  | SUBTOTAL | $ 8564 |
|  |  |  | DISCOUNT | $ 857 |
|  |  |  | (TAX RATE) | %5 |
|  |  |  | TAX | $385.35 |
|  |  |  | Invoice Total: | $8092.35 |

TERMS:  Please pay by Please Pay by 05/01/2021

## Maintenance and Rates:

Contracted maintenance begins 2 weeks after site launch. Maintenance is priced at $135 per month and will be billed monthly. Any major site changes will be evaluated and determined with client approval. If major site changes are estimated to extend outside of scheduled maintenance periods, additional contract agreement(s) will be created.

## Web Hosting and Domain:

The customer apprehends that any Website hosting service obliges a separate contract and is a separate contract with a website hosting service. The customer owns their domain.

## Changes:

After the web pages are created, the schedule required to make considerable changes to the client-submitted text will be extra, billed per Hour to be finalized.

## Completion Date:

Fees to J.A.R.S. Web Design is owned and accounts payable on the following schedule: 50% is received at the start of the project (the subject of project approval), and 50% must be paid before launching the website.

## Payment:

J.A.R.S. Web Design retains the right to eliminate web pages from broadcasting on the Internet until final payments are made. If a collection shows vital, the customer agrees to pay all fees incurred by that process.

## Assignment of Project:

J.A.R.S. Web Design retains the right to appoint subcontractors to this project to guarantee on-time achievement.

## Copyright and Trademarks:

The customer represents J.A.R.S. Web Design and completely warranties any constituent of the script, graphics, pictures, designs, trademarks, or other artwork provided to J.A.R.S. Web Design. The customer owns for inclusion in this website, or that the customer has authorization from the legal owner to the user each of these essentials and will hold safe, safeguard, and secure J.A.R.S. Web Design and its subcontractors from any claim or suit appearing from the client's use of such essentials provided.

## Budget Tracking:

The period performed on the project is followed through business time logs, and the financial plan budget is then added to a Microsoft Word Document with a comprehensive financial plan.

## Copyrights of Website:

Copyright to the website's professional manufactured work generated by J.A.R.S Web Design and is retained by  J.A.R.S Web Design. Upon final payment of this agreement, the customer is allocated permissions to use as a website the Design, graphics, and text contained in the completed manufactured webpages.

## Agreement:

The contract in this "Terms and Conditions" establishes the sole contract amongst J.A.R.S Web Design and the customer involving the website. A written alteration order must approve any extra work not stipulated in this contract.

All prices stipulated in this contract will be fulfilled for two months after both parties sign this contract. Continuous provisions after that time will oblige a new contract.

By signing this, you agree and understand the terms above:

X______________________________________________

Customer Print Name

X_Rosalind Scott, Founder and Owner of The Nail Hive_    03/30/2021

Customer Signature                                                                                   Date

X____JARS WEB DESIGN___________________________    03/30/21

J.A.R.S. Web Design Signature					Date

# Appendix:

## Detailed Schedule:

| Detailed Schedule |  |  |
| --- | --- | --- |
| Phase | Dates | Work: |
| Phase 1: Discovery & Overview |  |  |
| Part 1 | 2/24/21- 3/2/21 | Discovery - Audience Analysis Report - Competitive Analysis Report - Client Survey-Blank - Client Survey-Completed |
| Part 2 | 3/3/21- 3/9/21 | Clarification - Creative Brief - Mission Statement - Project Goals |
| Part 3 | 3/10/21- 3/30/21 | Project Planning - Project Scope - WBS - Schedule Overview/Detailed - Budget Overview/Detailed - Invoice - Client Approval Forms - Client Change Forms |
| Phase 2: Develop Website Structure |  |  |
| Phase 2 | 3/31/21- 4/6/21 | Develop Website Structure - Site Structure - Site Map - Content Outline & Delivery Plan - Wireframe - Naming Conventions - Navigation Structure - User Scenarios & Paths |
| Phase 3: Design Visual Interface |  |  |
| Phase 3 | 4/7/21 - 4/13/21 | Design Visual Interface - Templates and Mockups - Style Guidelines - User Experience - Functionality & Flow Confirmation |
| Phase 4: Development |  |  |
| Part 1 | 3/14/21 - 4/27/21 | Development - Develop Website Content - Content - Security Features - Accessibility And Web Standards - Responsive Web Design - Search Engine Optimization - Markup |
| Phase 5: Site Announcement & Final Review |  |  |
| Part 3 | 5/4/21 | Maintenance and Testing - Site Announcement Plan - Site Testing - Customer Testing - Quality Assurance Testing - Client Quality Assurance Plan - Maintenance and Evaluation Plan |
| Part 4 | 5/11/21 | Launch - Hand off Packet - Client Presentation - Launch Site |

## WBS (Work Breakdown Structure Detailed):

| Phases: | Work: |
| --- | --- |
| Phase 1: | Discovery & Overview: |
| 1.1 | - Audience Analysis Report - Competitive Analysis Report - Client Survey-Blank - Client Survey-Completed |
| 1.2 | - Creative Brief - Mission Statement - Project Goals - Target Audience - Competitive Position - Creative Tone/Perception - Target Message |
| 1.3 | - Project Scope - Project Objectives - Schedule Overview/Detailed - Budget Overview/Detailed - Invoice - Details and Assumptions - Terms and Conditions - WBS |
| Phase 2: | Develop Site Structure & Design |
| 2.1 | - Research and Initial Concepts - Receive Information from Client - Brainstorming - Create Basic Structure - Header Section: Name of Business, Logo, and website links - Content Section: Home, Menu, Appointments, About, and Contact information. - Footer Section: Address, Phone number, Email, Social Media Buttons, and Copyright information. - Information Architecture - Site Map - Wireframe - Naming Conventions - Navigation Structure - Content Outline and Delivery Plan - User Scenarios and Paths |
| Phase 3: | Design Visual Interface |
| 3.1 | - Templates and Mockups - Style Guidelines - Color Scheme - Logo - Visual Elements and Artwork - Images from Client for Photo Galleries - Optimize Images - Typography - Functionality and Flow Confirmation - Cross-Device Compatibility - User Experience |
| Phase 4: | Development |
|  | - (If Needed) Select Framework and Database - Develop Website Content - Receive details from Client - Specials/Deals Page - Contact Page - About Page - Services Page - Home Page - Photo Galleries - Online Booking Form - Markup - Security Features - Secure Booking Form - Accessibility and Web Standards - Build RWD and SEO - Utilize Meta Tags (Viewport) - Utilize Keywords in Title and Alt Tags |
| Phase 5: | Site Announcement & Final Review |
| 5.1 | - Domain Name Registration - Search Engine Registration - Site Announcement Plan - Testing - Server Errors - Debug - Functionality - Customer Testing - Site Performance - Quality Assurance - Proofreading - Client Training - Client Presentation - Hand Off Packet - Deliver Site to Client - Launch Site - Maintenance & Evaluation Plan - Design, Content, and Functionality Updates - Support and Troubleshooting |

## Detailed Budget:

|  | Task Description | Hours |
| --- | --- | --- |
| 2/24/21 - 3/2/21 | Phase 1: Part 1: Discovery Documents | ($60/HR) |
| Jeanna Brault, PM | Audience Analysis | 4:30 |
| Ashley Giedd, CL | Competitive Analysis: > Industry Info, Grid Overview, Appendix Notes, Overall Rating | 3:00 |
| Riandria Gordon, PR | Competitive Analysis: > Summary, Approach, Competitive Overview, Recommendations | 3:00 |
| Sabrina Larson, WPS | Client Survey | 4:30 |
|  | Subtotal Work Hours | 15:00 |
|  | Actual Cost | $900 |
| 3/3/21 - 3/9/21 | Phase 1: Part 2: Clarification Documents |  |
| Jeanna Brault, PM | Creative Brief > Target Audience, Goals | 1:30 |
| Ashley Giedd, CL | Creative Brief > Competitive Positioning, Goals, Statement Overview | 1:00 |
| Riandria Gordon, PR | Creative Brief > Creative Tone | 1:30 |
| Sabrina Larson, WPS | Creative Brief > Statement Overview, Mission Statement, Goals, Target Message | 1:00 |
|  | Subtotal Work Hours | 5:00 |
|  | Actual Cost | $300 |
| 3/10/21 - 3/30/21 | Phase 1: Part 3: Project Planning Documents |  |
|  | Project Scope | 5:00 |
|  | Detailed Schedule | 5:00 |
|  | Detailed Budget | 6:00 |
|  | Work Breakdown Structure Document | 6:00 |
|  | Subtotal Work Hours | _ |
|  | Estimated Work Hours | 22:00 |
|  | Additional Fees, Costs, & Materials |  |
|  | Contract Fee | $80 |
|  | Estimated Cost | $1400 |
|  | Actual Cost | _ |
| 3/31/21 - 4/6/21 | Phase 2: Develop Site Structure |  |
|  | Site Map | 3:00 |
|  | Content Outline & Delivery Plan | 3:00 |
|  | Navigation Structure | 3:00 |
|  | User Scenarios and Paths | 3:00 |
|  | Subtotal Work Hours | _ |
|  | Estimated Work Hours | 14:00 |
|  | Estimated Cost | $840 |
|  | Actual Cost | _ |
| 4/7/21 - 4/13/21 | Phase 3: Design Virtual Interface |  |
|  | Templates and Mockups | 2:00 |
|  | Style Guidelines | 1:00 |
|  | User Experience | 3:00 |
|  | Functionality and Flow Confirmation | 2:00 |
|  | Subtotal Work Hours | _ |
|  | Estimated Work Hours | 18:00 |
|  | Estimated Cost | $1080 |
|  | Actual Cost | _ |
| 4/14/21 - 4/27/21 | Phase 4: Development |  |
|  | Develop Website Content | 8:00 |
|  | Build Responsive Web Design | 6:00 |
|  | Develop Security Features | 3:00 |
|  | Search Engine Optimization | 2:00 |
|  | Markup (Code) | 1:00 |
|  | Subtotal Work Hours | _ |
|  | Estimated Work Hours | 20:00 |
|  | Estimated Cost: | $1200 |
|  | Actual Cost | _ |
| 4/14/21 - 4/27/21 | Phase 5: Site Announcement & Final Steps |  |
|  | Site Testing | 4:00 |
|  | Quality Assurance | 3:00 |
|  | Maintenance & Evaluation Plan | 1:00 |
|  | Client Training | 2:00 |
|  | Subtotal Work Hours | _ |
|  | Estimated Work Hours | 10:00 |
|  | Estimated Cost: | $600 |
|  | Actual Cost | _ |
|  | Additional Costs |  |
|  | Domain Name Registration | $20/year |
|  | Search Engine Registration | $99/mo |
|  | Server Hosting | $20/month |
|  | Additional Markup | $1204 |
|  | Additional Upfront Cost | $2244 |
|  | Estimated Total Budget | $8264 |

## Creative Brief:

### Statement Overview

  - The Nail Hive, located in Wisconsin, is an upscale nail salon focusing on providing professional nail services in an enjoyable and relaxing environment. Our goal is to create a website where customers can be informed and give a glimpse of what The Nail Hive is all about.

### Mission Statement:

- Our mission is to give our customers gorgeous nail spa amenities in a compassionate, extravagant, and specialized atmosphere.

We aim to personalize our customers' wishes to give them the best possible experience with us.

We welcome comments to guarantee luxury and satisfaction and to encourage repeat business. Behind the scenes, we are aware of our customers' health by taking cleanliness very seriously.

We are equipped with high-grade sanitation tools and stringently apply correct sanitation procedures amongst our team. We only use the hand-picked merchandise and creams and offer a tranquil atmosphere with exceptional lighting, music, style, and materials throughout the nail spa. Our primary goal is to provide our customers a memorable and relaxing experience.

### Target Audience Profile

  - The Nail Hive's primary target audience is women between the ages of 35 to 54 who are seeking a relaxing, high-quality nail salon experience. An average customer in this group is married with exposable income and average to a basic internet/mobile expertise level. A majority of the Nail Hive's customers are within a local driving distance and enjoy the Nail Hive's pedicure services.

### Competitive Position

  - Our three biggest competitors are Cozy Nails and Spa, Sky Nails, and Pink Me Nails. These competitors have a website, multiple services, and many customers. We are ahead of them in offering outstanding customer service and providing professional service. Still, we are behind when offering a website that includes benefits and a photo gallery.

### Creative Tone

  - We want the website to be inviting and minimalist. Making room for pictures of our work to give clients a way to see why to visit us. Splashes of color here and there to accentuate the main attractions. Easy to read text and layouts to keep it easy to use for all ages. The website will have a friendly tone, making all know that the Nail Hive is a place for all to come and feel pampered!

### Target Message

  - There is nothing wrong with being addicted to nails!

### Goals

  - Drive traffic from Facebook viewers to visit The Nail Hive website in three months.

  - Increase 100 unique customer visits in three months.

  - Create a modern, mobile-friendly website and have it launched by May 2021.

  - Showcase the Nail Hive's offered services and brand quality.

Signed: 	Date: March 9, 2021

Rosalind Scott

Founder and Owner, The Nail Hive